## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 2022-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | two new members add | 3 | 4 | 4 | 4*2*4=33 | Siyuan Wan, Yibo Wang | 2023-09-21 | update the front and back end team division | We have two new members: Siyuan and Yibo | finished
| Lack of motivation or responsibility | tasks are too hard, members become procrastinated | 3 | 5 | 4 | 4*2*4=34 | No | 2022-09-28 | Members motivate each others | Members are full of motivation | open
Communication | duplicate work | members may work on the same part, doing duplicate works | 1 | 3 | 4 | 4*2*4=35 | No | 2023-09-28 | Delete the duplicated works | Members have their own part | open
| worked on wrong components | members do the tasks not belongs to them | 1 | 1 | 4 | 4*2*4=36 | No | 2023-09-28 | Give members other tasks if their tasks were done by others | Members work with the assigned work | open
| useless work | members do some tasks no related to project | 1 | 3 | 4 | 4*2*4=37 | No | 2023-09-28 | All work is useful | All work is useful | open
| inconsistent work | members cannot follow with the team well | 2 | 5 | 4 | 4*2*4=38 | No | 2023-09-28 | All members follow with the team perfectly | All work is consistent | open
Requirements | unclear requirements | Team cannot figure out the requirements | 1 | 2 | 4 | 4*2*4=39 | No | 2023-09-28 | Figure out all requirements so far | All clear | open
| scope creep | Team add features gradually | 2 | 3 | 4 | 4*2*4=40 | No | 2023-09-28 | No so far | No | open
| constant requirements changes | Team need to change the constant requirements | 1 | 1 | 4 | 4*2*4=41 | No | 2023-09-28 | No so far | No | open
Management | improper task assignments | Team members get unbalanced work load | 1 | 4 | 4 | 4*2*4=42 | No | 2023-09-28 | No improper task assignments so far | No | open
| improper planning | Product does not have a clear feature | 1 | 5 | 4 | 4*2*4=43 | No | 2023-09-28 | No improper planning so far | No | open
| lack of management skills | Team leader doesn't know how to manage the tasks | 1 | 1 | 4 | 4*2*4=44 | No | 2023-09-28 | Team leader is great to lead member to work | No | open
Technology competence | Not familiar with the framework used | Members are not familiar with MERN | 4 | 4 | 4 | 4*2*4=45 | No | 2023-09-28 | Schedule peer coding, experienced members teach noob member | Members are learning MERN | open
| Not familiar with the programming language used | Team members never or seldomly use Javascript | 4 | 4 | 4 | 4*2*4=46 | No | 2023-09-28 | Doing peer coding meeting. Members teach each others | Members are learning Javascript | open
| Not familiar with unit testing | No one in the team have testing experience | 3 | 2 | 4 | 4*2*4=47 | No | 2023-10-19 | Members help out each others | Do testing | open
| Other technology incompetence | Members are not familiar with pivotal Tracker or other project managerment tools | 4 | 1 | 4 | 4*2*4=48 | No | 2023-10-19 | Members help out each others | Members are learning tools | open
| Not familiar with Git | Members are not familiar with Git commands or branch | 4 | 2 | 4 | 4*2*4=49 | No | 2023-09-28 | Members help out each others | Members are learning and trying out Git | open
Design and implementation | Improper design | wrong design in project that cannot be functioned | 1 | 5 | 4 | 4*2*4=50 | No | 2023-09-28 | Members help out each others | Members are learning and trying out Git | open
| improper technology stack | Tech stack is not suitable for project | 1 | 1 | 4 | 4*2*4=51 | No | 2023-09-28 | Members help out each others | Members are learning and trying out Git | open
| Messy code | too much redundant code | 3 | 2 | 4 | 4*2*4=52 | No | 2023-11-09 | reduce the redundant code | polish the code | open
Testing | Not enough testing | Members don't test enough, bugs may happned | 2 | 3 | 4 | 4*2*4=53 | No | 2023-12-07 | Do more test, keep some time after deelopement | Do testing | open
Integration and deployment | Not enough time for integration and deployment | Members run out of time developing and have no time to integrate or deploy | 2 | 2 | 4 | 4*2*4=54 | No | 2023-12-08 | Kepp some time for integration adn deployment | Do the intergrationa dn deployment | open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.