## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/21-9/28 | Project development ideas. Clear division and familiarization with individual parts. | None | During this iteration, our team welcomed two new members. Their inclusion brought fresh perspectives and skills to the group, but also necessitated adjustments in team dynamics and roles. | Project development ideas. Clear division and familiarization with individual parts. | 0 | 0 | 0 | 0 | 0 | 33 hours | 30 hours | 3 hours | 33
1 | 9/29 - 10/19 | Finished front-end UI design and development; Setup connection with OpenAI; Built up back-end routes and controller methods | User document homepage: React Desturcture method. Bug fix with Google Sign in; Bug fix with LangChain | None | Learn error status knowledge for next stage. | 0 | 8 | 0 | 0 | 0 | 240 hours | 228 hous | 12 hours | 116 | 8 | 20 | 18 | 20 | 36 | 0 | None

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## Wenhao(Chris)
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | Sept5 - Sept 11 | 0
2 | Sept 11 - Sept 18 | 0 | 4 | 0 | 0 | 3
3 | Sept 18 - Sept 25 | 6 | 3+3 | 3+3 | 0,1 | 2 | 1
4 | Sept 23 - Octo 2 | 6 | 3+3 | 3+3 | 0,1 | 3 | 1
5 | Octo 2 - Octo 9 | 6.5 | 4+2.5 | 4+2.5 | 0,2,3,5 | 2 |  | 2 | 2 |  | 1 |  |  |  |  | plan to resaerch more on LangChain and Google-Sign-In | Finish implementing Google-Sign in | 5
6 | Octo 9 - Octo 16 | 5+2.5 | 5+2.5 | 5+2.5 | 0,2,3,5,6 | 1 |  | 1 | 1 |  | 1 | 1 |  | Designed data communication between client, back and database |  |  | Keep working on back end get and post routes | 3
7 | Octo 16 - Octor 23 | 5+2 | 5+2.5 | 5+2.5 | 0,2,3,5 | 3 |  | 2.5 | 1.5 |  | 1 |  |  | Designed back-end API routes and controllers.
8
9
10

## Yichen
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | Sept5 - Sept 11 | 6 | 2 | 4 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 5
2 | Sept 11 - Sept 18 | 10 | 2 | 8 | 0,1,2,3,5 | 2 | 2 | 2 | 2 | 0 | 2 | 0 | 0 |  | 0 | 0 | learn tech | 5
3 | Sept 18 - Sept 25 | 10 | 2 | 8 | 0,1,2,3,5 | 2 | 2 | 2 | 2 | 0 | 2 | 0 | 0 | learn tech | 0 | 0 | frontend | 5
4 | Sept 23 - Octo 2 | 10 | 2 | 8 | 0,1,2,3,5 | 2 | 2 | 2 | 2 | 0 | 2 | 0 | 0 | frontend | 0 | 0 | frontend | 5
5 | Octo 2 - Octo 9 | 10 | 5 | 6 | 0,1,2,3,5 | 2 | 2 | 2 | 2 | 0 | 2 | 0 | 0 | frontend | 0 | 0 | frontend | 5
6 | Octo 9 - Octo 16 | 10 | 6 | 6 | 0,1,2,3,5 | 2 | 2 | 2 | 2 | 0 | 2 | 0 | 0 | frontend | 0 | 0 | presentation | 5
7 | Octo 16 - Octor 23 | 10 | 7.5 | 6 | 0,1,2,3,5 | 2 | 2 | 2 | 2 | 0 | 2 | 0 | 0 | presentation | 0 | 0 | iteration2 | 5
8
9
10

## Nicholas
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | Sept 11 - Sept 18 | 2 | 2 |  | 7 - research similar products, discuss with potential teammates about idea | [7 empty] | 2 | 1. Research about flow for the product | 1. Have another product in mind, have to compare which 1 is more feasible |  | 0 - figure out which product we want to create
2 | Sept 18 - Sept 25 | 2 | 2 |  | 5 - discuss product and planning with teammates 6 - set up git | [5 empty] | 1 | 1 |  | 1. Decided on product, figure out functional requirements and features 2. Set up git, discussed workflow for lab1 assignment
3 | Sept 23 - Octo 2 | 8 | 7 | 1 | 1 - discussed features of application 6 - helped setup git and taught git commands to teammates 7 - prepared iter0 presentation |  | 2 |  |  |  |  | 2 | 3 | 1. Create iter0 presentation 2. Discussed requirement analysis of product 3. Discussed what to accomplish for each iterations
4 | Oct 2 - Oct 9 | 10 | 10 |  | 0 - reading through langchain documentation and checking sample langchain repositories 7 - Review teammate's code and help debug | 4 | [6 empty] | 6
5 | Oct 9 - Oct 16 | 10 | 10 |  | 3 - testing using OpenAI API and check output 7 - Review teammate's code and help debug |  |  |  | 4 |  |  |  | 6
6 | Oct 16 - Oct 23 | 6 | 6 |  | 0 - learning node 7 - Review teammate's code and help debug, create iter1 ppt | 2 | [6 empty] | 4
7
8
9
10
11
12
13
14
15
16
17

## Guancheng
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/07-09/14 | 5 | 5 | 0 | g | 2 | 1 |  |  |  | 1 |  | 1 | 1. set up git and set up new branch 2. working on the project requirements | 1.not familar with Git 2. communication is not clear | 1. finish git tutorial 2. communicate more frequently | 0 - lean Git 2- make sure the plan and road map | 5
2 | 09/14-09/21 | 10 | 5 | 5 | 0 - Learn Git, Node.js, React 1 - make sure the requirements based on the design 2 - knock down the front end and back end design 6 - set up git, coding , running environment 7 - split the tasks to front end team and back end team | 4 | 1 | 2 |  |  |  | 2 | 1 | 1. try merge branch and slove the conflict 2.split the team 3. knock down design | 1. not familar with MERN | 1. finish Git tuttorial 2. set up git | split the team and knock down the front and end planning | 8
3 | 09/21-09/28 | 10 | 2 | 8 | 0 - Learn MERN stack 5 - make project plan and road map 6 - set up git 7 - Finsih Iter0 presentation slides and edit | 4 |  |  |  |  | 2 | 1 | 3 | 1. learn MERN |  |  | Start the front end coding session | 8
4 | 09/28-10/05 | 10 | 2 | 8 | 0 - Learn MERN 3 - Being Coding the front end 4 - debug and testing temp code | 0 |  |  | 8 | 2 |  |  |  | 1. Learn React and start coding the front end |  |  | continue working on the front end | 8
5 | 10/5-10/12 | 10 | 2 | 8 | 0 - Learn React 3 - finishing the UI 3- making Iter I slides 4 - test out Langchain | 1 |  |  | 7 | 2 |  |  |  | 1. finish the UI part coding |  |  | finishing the slides and ready for the presentation | 9
6 | 10/12-10/19 | 10 | 2 | 8 | 0 - learn Node.js 3 - edit the slides 4 - testing front end job | 2 |  |  | 2 | 6 |  |  |  | 1. finish the iteration I documents |  |  | start backend coding | 7

## Yibo Wang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | Sep/5 - Sep/11 | 0 | 0 | 0 | n/a | / | / | / | / | / | / | / | / | / | / | / | / | /
2 | Sep/12 - Sep/18 | 0 | 0 | 0 | n/a | / | / | / | / | / | / | / | / | / | / | / | / | /
3 | Sep/19 - Sep/25 | 16 | 10 | 6 | 1 - set up git 2 - research through mantine library 3 - writing documents | 2 | 6 | 2 | / | / | / | / | / | 1. set up git 2. working on iteration 0 powerpoint 3. writing SPPP | 1. not familiar with git 2. new to webpage development | 1. learn git on youtube 2. learn web development on odin 3. talk to group leader | 1. get git working 2. figure out requirements 3. build up skelaton of document page | 10
4 | Sep/26 - Oct/2 | 24 | 18 | 6 | 1 - designing docuemnt UI 2 - learning CSS and react 3 - taking meeting minute 4 - requirement analysis | 6 | 10 | 0.5 | 1.5 | / | / | / | / | 1. building page UI for document page 2. taking meeting minute | 1. not familiar with css and react | 1. keep learning web page building | 1. getting more familiar with css 2. learn form group leader | 20
5 | Oct/3 - Oct/9 | 18 | 12 | 6 | 1 - implementing document UI 2 - learning CSS and react | 6 | 6 | / | / | / | / | / | / | 1. building page UI for document page | 1. getting elements into places they were designed | 1. keep learning web page building | 1. geting most part of layout done | 10
6 | Oct/10 - Oct/16 | 25 | 17 | 8 | 1 - debuging and adjusting UI 2 - writing documents | 15 | 2 | / | / | / | / | / | / | 1. finishing page UI for document page, test, and debug. remove redundancy | 1. the code doesnt work sometimes, it is hard to get the function work as it supposed to | 1. looking for peer code and review | 1. finish UI implementing | 20

## Siyuan Wan
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | Sept 5 - Sept 11 | 0 | 0 | Not in | 0
2 | Sept 11 - Sept 18 | 6 | 5+1 | Not in | 0,6 | 5 | [5 empty] | 1
3 | Sept 18 - Sept 25 | 8 | 5+3 | 6 | 0,1 | 5 | 3
4 | Sept 25 - Octo 2 | 8 | 5+3 | 6 | 0,1 | 5 | 3
5 | Octo 2 - Octo 9 | 20 | 20 | 6 | 0,1,2,3,4,5 | 12 | 2 | 4 | 2 | 2 | 4
6 | Octo 9 - Octo 16 | 22 | 22 | 8 | 0,1,2,3,4,5 | 15 | 2 | 5 | 2 | 4 | 2
7 | Octo 16 - Octor 23